## Slide 1
Digital Programme Update: December 2018
Dan Howard
Chief Information Officer
4 December 2018

## Slide 2
Summary
  Final stages of PRISM development
  Good stakeholder engagement – clinics and EPRS suppliers
  Data migration stage 1 going well, stage two has presented some challenges
  Communications strategy ongoing
  RITA (internal system to interrogate data) to be written in January
  Will seek ‘Approval to proceed’ once development, user/performance testing, data migration validation checks all complete and satisfactory
  Launch end-January
  Planning ‘Choose a Fertility Clinic’ follow-on refresh work

## Slide 3
PRISM / APIs development
  Approaching end ‘view and edit’ and reporting
  Then onto deletions, extended validation, revalidation and changing roles
  ‘Bug’ resolution ongoing
  Good engagement with sector and EPRS suppliers
  User Acceptance testing due to start early January

## Slide 4
Data Migration
  Stage 1 – Transfer of data
  Excluding gamete movements – in excess of 99%
  Stage 2 - Migrated data produces identical results as before
  94 – 100% correct matches
  Algorithm needed for CaFC and Gamete Movement (EggBatchID) challenging
  EggBatchID links data and treatment cycles – needed to allow traceability of gamete movements
  EggBatchID algorithm complete before launch and we are working on contingencies

## Slide 5
Data Migration impact
  Opening the Register requests
  Good match between data
  Bespoke systems and data - additional manual processes to be introduced e.g double checking against old register and clinics for 6 months
  Sample of historic responses to be checked against migrated data
  Structural changes
  New register very different to old register – validation rules, relational database, logical structure
  Can’t map directly across by moving data from box to box
  Longitudinal linkages must be correct
  PQs
  Good match between live register and migrated data
  Small amount of further work needed
  Our PQ responses always reflects evolutionary nature of our data over time

## Slide 6
Choose a Fertility Clinic
  Provides a performance view of clinics on our website including success rates
  Data typically updated every 6 months
  Last update 2 years ago
  Backlog of data to be checked by clinics following go live – closely supported by register team
  Communication strategy to include system element and information element
  Potential refresh of CaFC in autumn 2019
  Validation rules means ‘right first time’ data in the future
  Potential for much more frequent CaFC refresh and/or real-time reporting

## Slide 7
Governance and financial
  ‘Approval to proceed’ during January 2019 based on risk assessment
    Reputational
    Business
    Financial
  Launch at end January 2019
  Programme forecast - within capital budget of £500k
  Any future significant issue between now and launch to be discussed between AGC chair and key staff

## Slide 8
www.hfea.gov.uk